## Start Here
IncuBrix PS4 — Submission Form Draft
Purpose | Draft worksheet based on the supplied PS4 brief. Transfer to the official workbook downloaded from the assessment pack.
Project | Distribution: Long-Tail Destination Network
Candidate / email | Fill in yourself; do not place personal data in a public repository.
Repository URL | NOT AVAILABLE — create private GitHub repo and grant admin@incubrix.com reviewer access.
Live demo URL | NOT DEPLOYED — do not enter a guessed URL. This is a blocker if the form requires a live demo.
Demo video URL | NOT RECORDED — record an unedited video (max 8 minutes) only after verifying the app.
Highest level completed | Prototype only; Core not completed.
Overall status | Partial prototype; all must-haves do not pass.
Test evidence | 12 unit tests passed against emitted JavaScript; npm install/typecheck/API runtime/Compose not verified. See test-pack/unit-test-output.txt and REPORT.md.
AI use | OpenAI ChatGPT (GPT-6) assisted with brief interpretation, code/test/document edits and submission drafting. No AI API is called by runtime.
External AI API cost | USD 0 for runtime; development tool subscription costs not assessed.
Important | Do not claim full Core, live platform certification, public demo, deployment or test results that have not been verified.

## Must-haves
# | Requirement | Status | Evidence / file | Notes
1 | Exact connector contract | Partial | src/server.ts; src/connectors.ts; openapi.yaml | Route/method dispatch exists; evaluator contract not run and native adapters absent.
2 | Six Core connectors certified | No | test/connectors.test.ts; REPORT.md | Only simulated lifecycle; no real platform certifications. Assisted mode is manual pack.
3 | Configuration, not code | Partial | src/server.ts; src/catalogue.ts | Destination rows and catalogue imports are in memory only.
4 | Rules before every post | Partial | src/rules.ts; test/rules.test.ts | Unit rules tested; API integration/concurrency not verified.
5 | No spam, safe cleanup, 429 handling | Partial | src/connectors.ts; REPORT.md | Simulation default and bounded webhook retry; native 429 reset/10-minute cleanup not implemented.
6 | Safe retries | Partial | src/server.ts; src/connectors.ts; test/connectors.test.ts | In-memory idempotency; no durable exactly-once guarantee.
7 | Secrets protected and simulation mode | Partial | .env.example; src/server.ts; AI_USE.md | Environment secrets and simulation default; deployment security not tested.
8 | Local Lemmy/Ghost and mock servers in Compose | No | docker-compose.yml | Compose starts API only; local Lemmy/Ghost missing.
9 | Integration Standard and live demo | No / Partial | openapi.yaml; src/batch.ts; REPORT.md | Some API/job/error/log/manifest/batch pieces exist; S3-compatible files, full tests and live demo missing.

## Levels
Level / item | Status | Evidence / notes
Core | Not completed | Core requires every must-have and real destination certification evidence.
Advanced: CSV catalogue import | Partial | CSV parsing, normalized URL/platform dedup, row-level errors and keyword relevance score exist; reachability/enrichment and 1,000-row benchmark absent.
Advanced: AI rule capture with human approval | No | Not implemented.
Advanced: destination tailoring | No | Not implemented.
Advanced: three extra connectors | No | Not implemented.
Outstanding: recommender precision@10 | No | Not implemented or measured.
Outstanding: metrics on three connectors | No | No live platform metrics adapters.
Outstanding: recertification/demotion | No | Not implemented.
Outstanding: 150 researched destinations | No | No researched catalogue included.

## Integration
# | Integration Standard | Status | Evidence / notes
1 | One-command start and test | Partial | Docker Compose and test scripts exist; Compose only starts API, dependencies were unavailable, full test command not verified.
2 | OpenAPI 3.1 | Partial | openapi.yaml drafted; not validated against a running API.
3 | Background jobs | Partial | Publish/catalogue/certification return 202 and expose in-memory job status.
4 | Idempotency-Key on every POST | Partial | Publish, catalogue import, certification and destination creation require keys; connector contract methods vary and durability is in-memory.
5 | Clear JSON errors | Partial | Shared error envelope and error codes exist; API integration not verified.
6 | Configuration via env/config | Partial | .env.example; some limits/manifests remain in source code.
7 | Files in/out via S3-compatible storage | No | No upload/URL ingestion or S3/MinIO output storage.
8 | Structured logs and health | Partial | JSON logs with correlation ID plus /health and /ready; not runtime-tested.
9 | Output manifest | Partial | Basic provider/version/settings/timing/cost/warnings/rights fields; no model provider because no model is called.
10 | Batch runner | Partial | CLI runner exists; HTTP run has not been executed here.

## Metrics
Metric | Measured value | Evidence / caveat
Unit tests | 12 passed, 0 failed | test-pack/unit-test-output.txt; emitted JS test run only, not npm test.
npm install | Failed (EAI_AGAIN) | Environment could not resolve registry.npmjs.org.
Typecheck | Not verified | Missing @types/node because dependencies could not be installed.
HTTP integration tests | Not run | Express dependency not installed in this environment.
Docker Compose startup | Not run | Docker unavailable in this environment.
Real destinations certified | 0 | No external test instance/account configured.
Simulated publication success rate | Not measured | No batch benchmark run against API.
Duplicate posts under timeout retry | Not measured for external platform | Simulation ID deterministic; external exactly-once not guaranteed.
Rule violations caught/missed | Not fully measured | Unit tests cover selected rule cases only.
Catalogue rows imported | Unit test: 1 accepted, 1 duplicate, 2 errors | test/catalogue.test.ts; not a 1,000-row benchmark.
Recommendation precision@10 | Not measured | No recommender or labeled set.
External AI API cost | USD 0 | Runtime does not call an external AI API.
Cost per 1,000 real publications | Not measured | No real publications.

## Hard Cases
Case | Status | Evidence / notes
Timeout then retry with same idempotency key | Partial | Deterministic simulated IDs tested; no injected external timeout test.
429 response with reset time | Partial | Webhook retry reads reset/retry-after with bounded retries; not integration-tested.
Expired token | Not tested | No real native auth adapter.
Platform content rejection | Not tested | Error mapping exists by code; no live provider response test.
Title/body over limits | Unit-tested | test/rules.test.ts catches title overflow; body overflow rule implemented.
Media unsupported | Not implemented | No destination media-type validation.
Frequency cap second post | Unit-tested | test/rules.test.ts.
Self-promotion blocked | Unit-tested | test/rules.test.ts.
Platform schema drift/demotion | Not implemented | No recertification/demotion logic.
CSV duplicates, bad URLs and unsupported platforms | Unit-tested | test/catalogue.test.ts.
Partner revokes permission | Not tested | No revocation polling workflow.
AI disclosure required | Unit-tested | test/rules.test.ts checks missing disclosure.

## Final Checklist
Submission item | Status | Action
Official PS4 Excel workbook | Not in current workspace | Download the original workbook from the Google Drive assessment pack and transfer these answers.
Private GitHub repository | Not created/pushed | Create repo, push project, grant admin@incubrix.com access.
Working live demo URL | Not deployed | Deploy only if you can verify it; never invent a URL.
Access token/instructions | N/A until demo exists | Do not share secrets in the repo or video.
Unedited demo video ≤ 8 minutes | Not recorded | Follow DEMO_SCRIPT.md after the app runs; preserve failures honestly.
README.md, openapi.yaml, REPORT.md, SOURCES.md, AI_USE.md | Drafts included | Review against actual final code and run results.
Test pack | Partial | Contains unit output and API request pack; API pack not executed here.
Certification pack | Simulation only | No real certification evidence available.
Declaration | Candidate action required | Read carefully and sign only if true.